## Slide 1: Research on Risk and Estimating NCHRP Research Report 1025 Contingency Factors to Account for Risk in Early Construction Cost Estimates for Transportation Infrastructure Projects
August 22, 2023
H. David Jeong, Ph.D.,
Texas A&M Transportation Institute
Texas A&M University

## Slide 2: NCHRP Research Report 1025: Contingency Factors to Account for Risk in Early Construction Cost Estimates for Transportation Infrastructure Projects
https://nap.nationalacademies.org/download/26829

## Slide 3: Why ? - Construction Cost Certainty !
Planning &Programming
Preliminary Design
Final Design
Construction
Scoping Phase
$
$
$
Early Estimate
Engineer’s Estimate
Actual Cost
Significant variation between early estimate and construction costs may lead to delaying, adding, or cancelling projects. Reallocation of funds or additional funds are needed.
Use of contingency factors is a good approach to addressing potential cost risks
Inconsistent and inaccurate application of contingency factors is a problem.

## Slide 4: NCHRP Research Report 1025
﻿A guidebook for developing early estimates of contingency factors for common project-related risks that affect construction costs.
The report will be of interest to those at state DOTs who are responsible for developing early construction cost estimates for projects, as well as for those who track program-level construction costs.
1. Introduction

## Slide 5: Report Structure
Introduction
Key Concepts – Construction Contingencies
Estimation Methods for Construction Contingencies
Major Risks for Construction Contingency Consideration
Guidance on Risk-Driven Approach for Estimating Construction Contingencies
Guidance on Historical Data-Driven Approach for Estimating Construction Contingencies
Guidance on Tracking and Monitoring Construction Contingencies

## Slide 6: Key Concepts and Components of Construction Cost Contingency
Inconsistencies in DOT manuals and guidelines
Inconsistencies in DOT practitioners’ perceptions (From Survey)
FHWA definitions adopted by the research team
2. Key Concepts – Construction Contingencies

## Slide 7: Major Elements of Construction Cost Estimate
2. Key Concepts – Construction Contingencies
Contingency - Unknown Knowns
Early Estimate = Base cost (itemized costs + allowance) + Contingency

## Slide 8: Construction Cost Contingency Coverage
No. | States | Risks realized during construction | Scope change | Minor item allowance | Scope creep
1 | Alaska | ● | □ | □ | □
2 | California | ● | □ | ● | □
3 | Colorado | ● | □ | ● | □
4 | Connecticut | ● | ● | X | □
5 | Florida | □ | □ | ● | □
6 | Georgia | ● | X | □ | □
7 | Idaho | ● | X | X | □
8 | Illinois | ● | X | ● | □
9 | Indiana | ● | X | ● | □
10 | Iowa | ● | □ | ● | □
11 | Michigan | □ | ● | ● | □
12 | Minnesota | ● | ● | X | □
13 | Montana | ● | ● | □ | ●
14 | Nevada | ● | X | X | □
15 | New York | ● | □ | ● | □
16 | North Carolina | ● | □ | □ | □
17 | Ohio | ● | □ | □ | □
18 | Pennsylvania | ● | X | X | □
19 | Texas | ● | □ | X | X
20 | Utah | ● | □ | ● | □
21 | Washington | ● | □ | ● | □
*Note: ●: Included, X: Not included, and □: Not specified |  |  |  |  | 
2. Key Concepts – Construction Contingencies

## Slide 9: Construction Cost Contingency – Definition
2. Key Concepts – Construction Contingencies
Construction Cost Contingency
  Unknown knowns
  Identified Risks
Construction Cost Contingency should not include
  Allowances (x)
  Major Scope Change (x)

## Slide 10: Construction Contingency Estimating Methods
3. Estimation Methods for Construction Contingencies
Contingency estimating methods
Probabilistic approach
Deterministic approach
Expert judgment
Fixed percentage
Sliding scale
Parametric estimating
PERT
Expected value
Monte-Carlo simulation
Deterministic approach
Probabilistic approach
Determine a single point estimate.
Appropriate when estimators are familiar with the type of the project from their experience.
Modeling uncertainty through statistical techniques.
Quantify risk impacts of probability with given project information.

## Slide 11: Contingency Estimating Methods
No. | State | Fixed Percentage | Sliding Scale | Expected Value | Monte Carlo Simulation
1 | Alaska |  | ● |  | 
2 | California |  | ● | ● | ●
3 | Colorado | ● |  | ● | 
4 | Connecticut |  | ● |  | 
5 | Florida | ● |  | ● | 
6 | Georgia |  | ● |  | 
7 | Idaho |  | ● | ● | 
8 | Illinois |  | ● |  | 
9 | Indiana |  | ● |  | 
10 | Iowa | ● |  |  | 
11 | Michigan |  | ● | ● | 
12 | Minnesota |  | ● | ● | ●
13 | Montana |  | ● |  | 
14 | Nevada |  | ● | ● | ●
15 | New York |  | ● | ● | 
16 | North Carolina | ● |  |  | 
17 | Ohio |  | ● |  | 
18 | Pennsylvania |  | ● |  | 
19 | Texas |  | ● | ● | ●
20 | Utah | ● |  |  | 
21 | Washington |  | ● | ● | ●
Total |  | 5 | 16 | 10 | 5
A review of cost estimating manuals and risk management guides
24% 76% 48% 24%
3. Estimation Methods for Construction Contingencies

## Slide 12: Deterministic approach
Fixed percentage of base cost
Sliding Scale
Expert Judgment
Project development stage | Contingency for roadway portion | Contingency for structure portion
Feasibility | +55% | +15%
Functional | +45% | +15%
Preliminary | +35% | +10%
At ROW | +25% | +10%
Final preliminary | +15% | +5%
Define decision problems
Recruit experts
Collect expert judgement
Analyze expert judgement
The simplest method.
A pre-determined percentage of the base cost.
A range of percentages.
Different ranges for different project conditions
Use estimator’s personal experience and judgement.
Reflect project specific characteristics.
(Pros) Simple, straightforward, and available when useful project information is insufficient.
(Cons) Accuracy is dependent upon cost estimator’s experience and expertise.
3. Estimation Methods for Construction Contingencies

## Slide 13: Probabilistic approach
Expected value
Risks | Occurrence (%) (A) | Impacts ($) (B) | Contingency ($) (A)*(B)
Known Hazardous Substance | 10 | 125,000 | 12,500
Coordination with Railroad Agencies | 10 | 50,000 | 5,000
Treatment of Water Discharged from Site | 3 | 400,000 | 12,000
Total |  | 29,500 | 29,500
Monte Carlo simulation
Identify project-specific risks and evaluate the probability and impact of the identified risks.
Require detail project information.
A sophisticated computer-based probabilistic method.
Provide more realistic contingencies through a range of possible values.
(Pros) Can reflect project-specific characteristics and conduct more flexible contingency estimates.
(Cons) Requires more time and effort to perform it.
3. Estimation Methods for Construction Contingencies

## Slide 14: Major Risks for Construction Contingency Estimating
4. Major Risks for Construction Contingency Consideration
1. Analysis of DOT risk checklists and risk registers
2. Find risks through discussions with DOTs
3. Assess risk occurrences and impact magnitude
4. Prioritize top 12 risks
The list of 23 risks
Determined top 12 risks
Top risk identification process

## Slide 15: Top 12 Major Risks
Ranking | Risk
1 | Utility issues
2 | Poor or incomplete project scope definition during the scoping phase
3 | Unexpected geotechnical issues
4 | Design changes
5 | Constructability issues
6 | Contractor availability and competition
7 | Railroad involvement
8 | Market conditions
9 | Late changes requested by stakeholders
10 | Project duration-related issues
11 | Errors in cost estimating
12 | Funding availability
Prioritized Top 12 risks
Utility issues
Unexpected geotechnical issues
Constructability issues
Railroad involvement
Late changes requested by stakeholders
Errors in cost estimating
Maintenance of traffic/work zone traffic control
Unknown or change in current asset conditions
Unexpected archeological or historic findings
Endangered/protected species encountered during construction
Issues with new materials, technologies, and methods
Coordination with other projects
Poor or incomplete project scope definition during the scoping phase
Design changes
Contractor availability and competition
Market conditions
Project duration-related issues
Funding availability
Hazardous materials encountered during construction
Coordination with government agencies
Surveys late or in error
Political risks
Unanticipated noise impacts and noise mitigation
23 risks for contingency estimating
4. Major Risks for Construction Contingency Consideration

## Slide 16: Workflow of Estimating Contingency for High Priority risks
5. Guidance on Risk-Driven Approach for Estimating Construction Contingencies
Help more thorough and comprehensive risk considerations.
Can reflect project characteristics rather than simply apply pre-defined percentages
1. Determine project characteristics, conditions, and environments
Is there any trigger?
Yes
Stop
3. Conduct qualitative assessment
4. Gather information & data from SMEs
5. Determine the probability and cost impact of the risk
Output the contingency amount for the risk
2. Contact subject matter experts (SMEs)
Is this risk significant?
No
Yes
Stop
No
6. (Optional) Select a response strategy & determine residual contingency

## Slide 17: Step 1
Gather key project information from scoping reports, including characteristics, conditions, and environments.
Identify the triggers for each of the top risks.
Step 1: Determine project characteristics, conditions, and environments
5. Guidance on Risk-Driven Approach for Estimating Construction Contingencies
1. Determine project characteristics, conditions, and environments
Is there any trigger?
Yes
Stop
3. Conduct qualitative assessment
4. Gather information & data from SMEs
5. Determine the probability and cost impact of the risk
Output the contingency amount for the risk
2. Contact subject matter experts (SMEs)
Is this risk significant?
No
Yes
Stop
No
6. (Optional) Select a response strategy & determine residual contingency

## Slide 18: Step 2
SMEs can provide valuable input and help validate project cost estimates.
Early cost estimators can contact relevant SMEs to get more information on the risks.
Step 2: Contact subject matter experts (SMEs)
5. Guidance on Risk-Driven Approach for Estimating Construction Contingencies
1. Determine project characteristics, conditions, and environments
Is there any trigger?
Yes
Stop
3. Conduct qualitative assessment
4. Gather information & data from SMEs
5. Determine the probability and cost impact of the risk
Output the contingency amount for the risk
2. Contact subject matter experts (SMEs)
Is this risk significant?
No
Yes
Stop
No
6. (Optional) Select a response strategy & determine residual contingency

## Slide 19: Step 3
Evaluate the risk’s significance on the project.
Assign scores from 1 to 5 to the risks in terms of occurrence probability and their impacts.
Step 3: Conduct qualitative assessment
5. Guidance on Risk-Driven Approach for Estimating Construction Contingencies
1. Determine project characteristics, conditions, and environments
Is there any trigger?
Yes
Stop
3. Conduct qualitative assessment
4. Gather information & data from SMEs
5. Determine the probability and cost impact of the risk
Output the contingency amount for the risk
2. Contact subject matter experts (SMEs)
Is this risk significant?
No
Yes
Stop
No
6. (Optional) Select a response strategy & determine residual contingency
Notes: I

## Slide 20: Step 4
Gather information and data from SMEs that can serve as a reference for early cost estimators.
Step 4: Gather information & data from SMEs
5. Guidance on Risk-Driven Approach for Estimating Construction Contingencies
1. Determine project characteristics, conditions, and environments
Is there any trigger?
Yes
Stop
3. Conduct qualitative assessment
4. Gather information & data from SMEs
5. Determine the probability and cost impact of the risk
Output the contingency amount for the risk
2. Contact subject matter experts (SMEs)
Is this risk significant?
No
Yes
Stop
No
6. (Optional) Select a response strategy & determine residual contingency

## Slide 21: Step 5 and Step 6
Estimate the risk’s impact (optimistic (O), most likely (M), and pessimistic (P)).
The average impact: I = (O+4M+P)/6.
Contingency amount = Pr x I
Step 5: Determine the probability and cost impact of the risks
5. Guidance on Risk-Driven Approach for Estimating Construction Contingencies
1. Determine project characteristics, conditions, and environments
Is there any trigger?
Yes
Stop
3. Conduct qualitative assessment
4. Gather information & data from SMEs
5. Determine the probability and cost impact of the risk
Output the contingency amount for the risk
2. Contact subject matter experts (SMEs)
Is this risk significant?
No
Yes
Stop
No
6. (Optional) Select a response strategy & determine residual contingency
Step 6: (Optional) Select a response strategy & determine residual contingency

## Slide 22: Overall Process of Historical Data-Driven Approach
6. Guidance on Historical Data-Driven Approach for Estimating Construction Contingencies
Use historical digital data for performing a construction contingency estimation.
Allow cost estimators to have confidence in their contingency numbers for a new project.
1. Historical Cost Data Collection
2. Data Cleaning and Pre-processing
3. Data Analysis and Project Characterization
4. Model Development
5. Apply Model to Projects

## Slide 23
Work Tasks for Historical Data-Driven Approach
1. Historical Cost Data Collection
2. Data Cleaning and Pre-processing
3. Data Analysis and Project Characterization
4. Model Development
5. Apply Model to Projects
Cost type | Ideal data attributes
Early estimate | Base estimate (major work items + allowance)
 | Construction contingency
Engineer’s estimate | The entire list of pay items with their quantities and unit prices
Final construction cost | The entire list of actual pay items with their quantities and unit prices
 | Change orders
Data collection and cleaning
Gather historical data over the project development phases.
Filter out projects that went through major scope changes.
<Cost data for data collection>
6. Guidance on Historical Data-Driven Approach for Estimating Construction Contingencies

## Slide 24
1. Historical Cost Data Collection
2. Data Cleaning and Pre-processing
3. Data Analysis and Project Characterization
4. Model Development
5. Apply Model to Projects
Classify project based on characteristics
RFB: The ratio of the final construction cost to the base cost estimate
Ex) Project type: New construction, Reconstruction, Resurfacing, Rehabilitation, and Relocation.
Project size: Small sized, Mid sized, and Large sized.
6. Guidance on Historical Data-Driven Approach for Estimating Construction Contingencies
Work Tasks for Historical Data-Driven Approach

## Slide 25
1. Historical Cost Data Collection
2. Data Cleaning and Pre-processing
3. Data Analysis and Project Characterization
4. Model Development
5. Apply Model to Projects
Contingency range estimation
Perform statistical analysis.
Probability distribution fitting.
Develop probability density functions (PDF) and cumulative distribution functions (CDF).
<PDF>
<CDF>
6. Guidance on Historical Data-Driven Approach for Estimating Construction Contingencies
Work Tasks for Historical Data-Driven Approach

## Slide 26: Case Study
Types | RFB |  | 
 | 10% | 30% | 50%
Roadway - new construction | 0.022 | 0.638 | 0.93
Roadway – reconstruction | 0.177 | 0.688 | 0.905
Roadway – resurfacing | 0.101 | 0.697 | 0.966
Roadway – rehabilitation | 0.132 | 0.652 | 0.888
Bridge replacement | 0.136 | 0.677 | 0.928
Bridge rehabilitation | 0.091 | 0.670 | 0.927
CDFs of six project types.
Cumulative probability refers to certainty about a given RFB.
RFB can be a percentage of base cost.
6. Guidance on Historical Data-Driven Approach for Estimating Construction Contingencies

## Slide 27: Case Study
①: Convert a construction contingency amount to the percentage of the base estimate.
②: Check cumulative probability from CDF curves to ensure the certainty of construction contingency.
Applications (Incorporate CDF into sliding scales)
6. Guidance on Historical Data-Driven Approach for Estimating Construction Contingencies

## Slide 28: Use of two approaches
Estimation: Risk-driven approach
Verification: Historical data-driven approach
Conduct risk identification and estimate their impacts on construction contingency.
Backcheck the amounts from risk-driven estimating.
Evaluate certainty for verification.
6. Guidance on Historical Data-Driven Approach for Estimating Construction Contingencies

## Slide 29: Construction Contingencies Tracking and Monitoring
7. Guidance on Tracking and Monitoring Construction Contingencies
Major milestone meetings for tracking and monitoring
(a) | (b) | (c) | (d) | (e)
End of project scoping | 30% design | 60% design | 90% design | Construction completion

## Slide 30: Iterative Process for Tracking and Monitoring Construction Contingencies
<MS Excel tool interface for contingency tracking and monitoring>
7. Guidance on Tracking and Monitoring Construction Contingencies

## Slide 31: Continuous Improvement of Construction Contingency Estimating Process
<Process for feedback loop for construction contingency estimating>
7. Guidance on Tracking and Monitoring Construction Contingencies
Notes: Continuous improvement of construction contingency estimating process
The information obtained from previous projects can significantly help improve planning and designing activities for future projects.
However, in practice, DOTs are poor at sharing, disseminating, and transferring knowledge due to a) the lack of a database that facilitates learning between projects and among people and b) the heavy reliance on an individual’s capability in capturing knowledge from previous projects.
Feedback loop for construction contingency estimating
1. Collect:
This step aims to acquire the data needed to calculate construction contingency estimating performance and recognize significant causes of performance results.
Since the uniqueness and complexity of highway projects establish a huge amount of different project-specific data, highway agencies can recognize and determine data that are necessary for construction contingency estimating.
2. Evaluate:
This step is to evaluate contingency errors.
𝐶𝑜𝑛𝑡𝑖𝑛𝑔𝑒𝑛𝑐𝑦 𝑒𝑟𝑟𝑜𝑟= (𝐴𝑐𝑡𝑢𝑎𝑙 𝑐𝑜𝑛𝑡𝑖𝑛𝑔𝑒𝑛𝑐𝑦−𝐸𝑠𝑡𝑖𝑚𝑎𝑡𝑒𝑑 𝑐𝑜𝑛𝑡𝑖𝑛𝑔𝑒𝑛𝑐𝑦 𝑎𝑡 𝑠𝑐𝑜𝑝𝑖𝑛𝑔 𝑝ℎ𝑎𝑠𝑒 )/(𝐴𝑐𝑡𝑢𝑎𝑙 𝑐𝑜𝑛𝑡𝑖𝑛𝑔𝑒𝑛𝑐𝑦)
3. Analyze:
This step aims to conduct an in-depth analysis that focuses on why contingency errors happened.
This step requires identifying root causes resulting from estimating errors and investigating the relationship between the identified root causes and project-specific characteristics.
4. Archive
This step encourages users to quickly access and update data for easy retrieval and adequate storage and management of insights for future projects.
The data archiving can be implemented through the standardization of data or information with database structure, a logical system for classifying data, and the adoption of a user-friendly update interface.
5. Disseminate and Apply
This step aims to disseminate obtained insights for better estimating construction contingency.
The obtained insights help highway agencies make appropriate adjustments for better construction contingency estimating.

## Slide 32
Feedback to djeong@tamu.edu